LIP Engagements Summary 1M1B Green Internship — Batch 7 Eco Bricks Creation for Plastic Waste Management Team: Planet Protectors ¦ S Ranjith (ASML24028) & B Lakshanyawanti (ASML25009) ¦ AMET University

# Overview

This document summarises all Learning in Practice (LIP) engagements completed by Team Planet Protectors during the 1M1B Green Internship, Batch 7. LIP engagements include all practical activities undertaken — from attending weekly sessions and collecting stakeholder feedback to physically creating eco bricks and publishing a Tableau dashboard.

# Week-by-Week Engagement Log

| Week | Date | Activity | Description | Mode | Engagements |
| --- | --- | --- | --- | --- | --- |
| Week 1 | 23 Feb – 28 Feb 2026 | Orientation & Project Selection | Attended the 1M1B Green Internship orientation webinar. Understood the internship structure, goals, and deliverable expectations. Selected the project topic: Eco Bricks Creation for Plastic Waste Management. Formed team 'Planet Protectors' with B Lakshanyawanti. | Online | 1 session |
| Week 2 | 01 Mar – 07 Mar 2026 | Research & Problem Understanding | Attended the Week 2 session. Researched the problem of plastic waste and the concept of eco bricks. Studied existing eco brick initiatives and their environmental impact. Defined project objectives and drafted the problem statement. Submitted Week 2 tracker. | Online + Self-study | 1 session + research |
| Week 3 | 08 Mar – 14 Mar 2026 | Stakeholder Feedback & Data Collection | Attended the Week 3 session. Designed and circulated a stakeholder feedback form using Google Forms. Collected responses from 15 respondents including students, faculty, and staff. Compiled and cleaned the dataset in Microsoft Excel. Submitted Week 3 tracker. | On-ground + Online | 15 stakeholders engaged |
| Week 3–4 | 10 Mar – 18 Mar 2026 | Eco Brick Creation (Physical Implementation) | Collected 1.5 kg of non-recyclable plastic waste from the college campus and nearby community. Cleaned and dried the plastic waste. Stuffed plastic tightly into 11 PET bottles using a rod to create eco bricks. Recorded weight and count of each eco brick created. | On-ground (Campus) | 11 eco bricks created |
| Week 4 | 15 Mar – 21 Mar 2026 | Data Analysis & Tableau Dashboard | Attended the Week 4 session. Uploaded the cleaned dataset to Tableau Public. Created visualizations including role distribution, eco brick awareness levels, project support, and plastic disposal behavior charts. Published the final interactive dashboard. Submitted Week 4 tracker. | Online | 1 dashboard published |
| Week 5 | 22 Mar – 29 Mar 2026 | Final Submission Preparation | Attended the final Week 5 session. Prepared the Final Project Report, Stakeholder Feedback Document, and Submission Template. Compiled all project deliverables into the Master Google Drive folder. Completed and submitted the Final Project Submission Form before the deadline. | Online | All deliverables submitted |

# Total LIP Engagement Summary

| Engagement Type | Count / Result |
| --- | --- |
| Weekly Sessions / Webinars Attended | 5 sessions |
| Stakeholders Engaged | 15 respondents |
| Eco Bricks Created | 11 bricks |
| Plastic Waste Diverted | 1.5 kg |
| Tableau Dashboards Published | 1 dashboard |
| Weekly Trackers Submitted | 5 trackers |
| Total LIP Engagement Count | 5 weeks of active participation |

# Declaration

We hereby confirm that all the activities listed above were genuinely carried out by Team Planet Protectors — S Ranjith and B Lakshanyawanti — as part of the 1M1B Green Internship, Batch 7. The engagements reflect our honest effort and contribution toward the project on Eco Bricks Creation for Plastic Waste Management.

— S Ranjith & B Lakshanyawanti  |  Planet Protectors  |  AMET University  |  Batch 7 —